## Work Plan Spreadsheet
Strategic Issue or Project (below); Prioritization Qs (at right) | Brief Project Description | Priority for your org? | Is it currently or potentially compatible with partners' missions and mandates, etc.? If no, what needs to happen? | Party/Parties Involved? | What project planning is in place? | What might the collaborative do to help? | Other partners outside collaborative needed? | What information on restrictions/resources might add to/impact the value of discussion? | What outcomes might be expected? (Consider downstream impacts) | NOTES:
Flood Control |  |  | NOTE: Ask the Corps what their project mgt/counsel believes they have authority to do & what activities/project actions would need new authority designated in next WRDA bill
Develop/explore additional flood plain capacity | Explore flood plain expansion at lower Cowlitz Horseshoe bend sump or cutoff in lower Cowlitz River | LCFRB, Port | Potential Section 404d or 408 review, depending on project and type of work/changes Section 404d review? Section 408 review: if will change how levees would function | DNR, FEDS/State |  | Request early input by regulatory agencies; Tribes
| Explore Sump at lower Toutle dredge spoil site | Port | potential section 404d or 408 review | DNR
| Explore Sump in sediment plain | LCFRB, Port | potential section 404d or 408 review | DNR | [5 empty] | Would like to see this revisited
Levee improvements | CDID#1 - Low spots on Cowlitz River Levee that need raising. | Port: levees important to infrastructure | Yes. Need to happen: Section 408 review, Section 205 - could be a source of federal funding | USACE (408), CDID, Cities of Longview, Kelso, Cowlitz Co., | Identified in COG planning document. working on getting into Cowlitz Co. comprehensive floodplain management plans. | Needs help to identify funding mechanisms, due dates, etc. (ie FEMA), Talk to City of Longview and Cowlitz County about infrastructure funding (ARP) and partnerships. | TBD | Identify funding sources |  | cost section 216, change conditions to authorized project, send a letter to Valerie Ringold. Requires an evalation as part of Corps analysis to make sure less than 1/10th of foot raise in flood elevations.
Other Projects of interest - see "related agency projects" tab
Modify Mossyrock Dam operations (to support fish recovery?) | How does flow regime affect sediment transport? Mossyrock plays a key role in flood control. USACE looked at scenarios; did not mobilize enough sediment to have a benefit | Would occur during relicensing: reach out to Tacoma Power ask about reliscensing timeline | regulated under FERC, settlement agreement, 401 req for instream flows - sideboards are pretty clear on the operations
Sediment Reduction |  | Port
Long-term dredging plan (for the Cowlitz R.) Intent: to have a process of the steps to ensure downriver safety, of processes/actions in place, communications re: flood risk level | Acquire disposal sites | Port | USACE developing a 20 yr dredge material management plan (DMMP) for the Columbia River Need to happen: USACE is finalizing …measure for a sediment trap for Toutle into the Cowlitz, & Cowlitz into Columbia, information forthcoming | County, USACE, State
| Seek agreement on sediment measurement timing and frequency | Port | USACE: will start bathometric survey in June 2022 | County, USACE, Kelso, Longview, Castle Rock, Diking Districts
Reconnect old channel at mouth of Cowlitz River Dikes to flush sediment at mouth of Cowlitz River |  | LCFRB | Need to happen: further clarification re: details of project
Develop sediment mgmt plan beyond 2035 |  | Port | Need to happen: id/clarify actions by local govt & USACE to develop the sediment mgmt plan beyond 2035 | USACE, local govts?
Explore collaboration opportunities between Army Corps and SLTCRC participants | Ongoing, via SLTCRC and other forums (as needed) | LCFRB, Port
Explore connections between participant/agency assets to address issues | Ongoing, via SLTCRC and other forums (as needed) | LCFRB, Port
Conduct evaluation of "grade building structures" in mudflow |  | LCFRB | Grade building structures: structures to capture sediment and increase grade. Need to happen: evaluation of their effectiveness--or, if available, a presentation on evalation's findings-->consider their utility & potential to scale up, in future | ASK Colin Thorne if these have been evaluated (present results?)
Toutle River Sediment Mgt.
Sediment Retention Structure (SRS) Storage Capacity Improvements | Brainstorming ideas beyond spillway crest raises. E.G. Serpentine channel (longer and less steep-grade building) this is part of the last part of the sediment monitoring plan/adaptive management plan. (USACE) Grade control Structures | Port | Serpentine channel (longer and less steep-grade building) this is part of the last part of the sediment monitoring plan/adaptive management plan. (USACE) Grade control Structures
Bank stabilization | Watershed scale restoration (combine bank stabalization and natural solutions to sediment movement and riparian floodplain restoration)Large wood structure upstream of SRS to slow bank erosion (and protecting Elk Habitat). Nature based solutions near the race track upstream of the Toutle (wood, brush and slash). Protect property and reduce sediment load. Helps to stabalize land in order to get plants to grow - not sure how much it impacts downsteam sediment. Cowlitz Conservation District - 3 potential projects sites in the lower stream. (need funding). LT1 (right at the lower Toutle- Toutle Park (bioengineering project) | Port | Signifigance of the reduction? Land owners - self fund?. Could expand the scope of the work. No place to put all the sediment, so better to dump it in many places. Need to know where the bank erosion is taking place (getting data on this upstream, but not aware of LIDAR downstream of SRS). repeat LIDAR downstream of SRS to get a sense of the hotspots downstream. (crowdsource data? Cowlitz Conservation District has been tracking this/channel migration and working with landowners) | WDFW/Port/LCFEG/Cowlitz Conservation District/USACE |  | Fee-in-lieu approach (J. Mallett idea): project funding possible via "fee in lieu designation" issued by USACE, WDFW, & 1 more WA agency TBD. JM applied for 6 mi of Cowlitz; 75 miles of river system open to same approach
Natural solutions to sediment movement | leverage nature's power to help ourselves - enhance, empower, and recruit nature. How does nature sequester sediment? In floodplains. (where can this be done in the Toutle-Cowlitz System?) See sediment as a resource? Source control, keep it in the hills (will help but not solve the problem). Geotubes (biodegradable geotextiles). | LCFRB, Port | identifying floodplain storage/reconnecting channels is politically/socially challenging- proceed carefully. |  |  | Fee-in-lieu approach (J. Mallett idea): project funding possible via "fee in lieu designation" issued by USACE, WDFW, & 1 more WA agency TBD. JM applied for 6 mi of Cowlitz; 75 miles of river system open to same approach |  | Produce information to help understand options
Riparian and flood plain restoration | Adopt codes to keep people out of flood plain? See where it floods & assess how to handle the flooding better. Volumen of material coming out of the rivers into the port (option for dredging as short term, dredging is one tool, use dredge material benificially?). Source control solution where we can employ structures to catch sediment, plant vegetation that help in source control. | LCFRB, Port | floodplain maps- (small work group?) |  |  | Fee-in-lieu approach (J. Mallett idea): project funding possible via "fee in lieu designation" issued by USACE, WDFW, & 1 more WA agency TBD. JM applied for 6 mi of Cowlitz; 75 miles of river system open to same approach
Recreation and Tourism
Improve Facilities/Coldwater Ridge (transforming the Visitor Center - Ray Y. ) working on expanding the vision to enable these options - working with forest service, gone through feasibility study. 45 million for everything, first phase is 5 million and is financially sustainable on its own. | Outdoor School & Adult Courses - (first phase, with some Yurts, trail infrastucture improvements, asking for funding in the next session after design and engineering is done) | LCFRB |  | MSHFI/ Tribal | Feasibility study in place, fundraising plan in process | build understanding of effort to find linkages | Private funding sources
Lodge and Cabin accommodations (kids from outdoor school and other visitors)
Campground & RV sites
Food concession
| Indigenous Cultural Sensitivity | LCFRB
| Natural History | LCFRB
Increase Braodband access | Extend broadband up 504 | Port | need to connect the fiber cable that the county has paid for. All the pieces are there, but needs finished. | [6 empty] | Would increase the attraction of tourism sites and increase the accessibility of information
Improve road system | High lakes one-way loop - concept as additional or alternative recreational opportunity. Add in- Evacuation route- through roads - up through green river valley connecting Mt Rainier to Mt Saint Helens. (loop road for Mt. Saint Helens) |  | How loop is designed it could involve access from Skammania County - Most is on private land and across the county border. Difficult to access now as there is multiple private ownership. | County, WSDOT, Private land owner? |  |  |  | Get clarification on project scope and intent
Increase public access and recreational opportunities | Elk Rock Sno-Park (Truck ramp access) WDOT - during the winter this becomes the center of snowmobiles (could use the ramp and develop a snowpark up there) |  | Collaboration between WSDOT and County. Private landowner above. Log trucks do use it sometimes, truck driver schools use it for training. May be better to use Maratta Creek.
| Maratta Creek Campground -Proposed campground (if practical). Area for potential development |  | on DNR owned property just off the highway
| Increasing fishing access on Toutle and Cowlitz Rivers - | LCFRB | Cowlitz County -some parcels that the County has on the Cowlitz (unimproved- needs resources) | DNR
| Increased camping and RV sites - Building camping and RV sites - up the corridor. |  | Eco-Park is the last camping location up the corridor. USFS Cooperation, allow RVs to purchase overnight stay? FS - ties into the larger planning (Coldwater,etc). County has an RV campground code- in the process of updating it now.
Salmon Recovery Program | Large Wood Structures | LCFRB, CIT | Yes - Multiple benefits from LWD structures: sediment control; fish habitat, fluvial complexity/stablity, thermal cooling, refugia, hyporheic flow, protect eroding streambanks, creating instream habitat. How it fits in with climate change and unsteady sediment load and changing weather patterns (example for other areas that have not had a volcano as their source but face similar upcoming challenges). | CFC - Instream wood bank, Tribes, WDFW, USACE, CCD, LCFEG | Compile/catalog ongoing & planned projects | Feasibilty studies for costs, feasibility, and likelihood of success for natural solutions.
| Invasive Weed Eradication | LCFRB, Port, CIT | Cowlitz Co. partners w/USFS to remove milfoil @ Coldwater Creek; also N. Fork on Japanese Knotweed (Jennifer Mendoza = contact at Co.) | Cowlitz Noxious Weeds Dept, CFC w/USFS; MSHVM, WDFW | Compile/catalog ongoing & planned projects | Mt. St. Helens Institute or Cascade Forest Conservancy (volunteers?)
| Side Channel Restoration | LCFRB, CIT |  | CFC - Instream wood bank, Tribes, WDFW, USACE, CCD,
| Bank Stabilization | Port, CIT | Compatible with other agencies; placement of wood structures used to stablize banks and protect riparian vegetation. Ongoing work that continues into another phase in 2023. Combination of both riparian and upland (not hardening). | CFC - Instream wood bank, Tribes, WDFW, USACE, CCD,
| Access to historic fish habitat in Spirit Lake area | LCFRB, CIT | Needs more study to make sure we maintain levels of protection for downstream communities and don't undermine the Corps downstream mandates at sediment control structure. How is the sediment in sediment plain affecting access/ passage / downstream sediment conditions? | USFS, USACE, universities (research side), CFC | EA with FONSI (CFC challenged, in 9th Circ seeking full EIS - is this still the case?) for temp road across pumice to do work at the Spirit Lake gate & some drilling. Earliest temp road would probably be summer 2023. | Study to understand the consequences of a daylighted channel to Spirit Lake (and considers public safety)
| Beaver Reintroductions | LCFRB, CIT | [7 empty] | Cowlitz Indian Tribe has been engaged in a beaver translocation program with the GPNF.
Fish Passage to under-utilized habitats | Collection facility at sediment retention structure | LCFRB, CIT | YES - compatible with agency mandates. New fish release sites in sediment plain. | WDFW, USACE, CIT, | Biological Opinion outlines the strategy for the new release sites and exploration of new release sites.
Hatchery production | Green River hatchery | LCFRB
Land acquistion adjacent to Mt.St. Helens Wildlife Area |  | LCFRB, CIT
Water Quality | Address elevated Temperatures via Riparian buffers, shade, shoaling | LCFRB, Port, CIT
| Turbidity | LCFRB, Port, CIT | 401 certification for changes to retention structure
Forest practices |  | LCFRB, CIT
Tribal resources |  | LCFRB, Port, CIT | [7 empty] | it would help to clarify what is meant by "tribal resources" to better determine specific projects.
Wetlands protection |  | LCFRB, Port
Identify opportunities for member organizations/agencies to cost-share with USACE on ecosystem restoration projects |  | LCFRB, CIT
Scientific Research and Data |  | In general, these projects are priorities for the Cowlitz Indian Tribe because scientific research and data to fill knowledge gaps will be critical in developing ecosystem-based strategies for sediment management.
Analysis of Sediment sources and specific causes | David Vorse, City of Castle Rock requests sit down meeting wi/USACE to discuss what's being done, where, why & when on sediment data collection & analysis. Looking for an explanation of the data collection plan & to increase communication, trust & mutual understanding. Currently sediment mgt = related only to monitoring level of protection of downstream levees, not other purposes but could be used by others for other purposes. | LCFRB, Port, CIT | Yes. USACE and affected Cities and jurisdictions need to get together and ask questions of each other to gain clarity and increase understanding. Sediment data collection methods, timing, applications of data needs to be dicussed to resolve a disconnect between USACE data collection and stakeholders observations. | City of Longview, City of Kelso, CDID #1, Cowlitz County ,City of Castle Rock, USACE, Port of Longview, USGS, Cowlitz/Wahkiakum Conservation District | On-going sediment data collection | Help organize and facilitate meeting |  | USACE past survey reports. Can be added to online data hub. Corps staff person Paul S. user and analyzer of the data. | More transparency, trust and understanding of all party needs.
Explore impacts of lateral erosion trends |  | LCFRB, CIT
Develop possible partners for cost share program with federal agencies to address |  | LCFRB, Port, CIT
Continued post-eruption scientific studies |  | LCFRB, CIT
Improve and document consequences of actions across the board - Evaluation process |  | LCFRB, CIT
Evaluate effectiveness of fish reintroduction work |  | LCFRB, CIT
General Activities
Explore areas where USACE technical assistance could benefit projects | Floodplain management services is 100% federal funds, submit ideas from local partners. very technical in nature, always associated with hydrology/hydraulic modeling. Also planning assistance for State agencies and tribes, geotech analysis, fish & wildlife, fisheries focused effort, navigation, 50% costshare. Tribes gets cost share waiver of $130k. Ecosystem Restoration, small program in continuing authories and large GI program. Sponsors have to come to the USACE for requests. | LCFRB, Port
Gain input from USACE on how Army Corps’ expertise might assist in addressing more localized problems |  | Port
Administration
Collaborative funding | Develop plan implementation through local agency partners | LCFRB, Port, CIT
Website/data library/hub | Establish and maintain collaborative web presence | Port
| Web links to relevant data | LCFRB, Port
| Sediment related reports | Port
| Conference presentations | Port
Explore development cost share models for future work |  | Port
Work toward development of an aspirational vision for the whole system |  | LCFRB, Port
Conduct checks into benefits of the communication venue/ is this an evaluation process? | ??? | Port
Communicate progress and efforts beyond the group | Report our on key needs/issues/projects of participants - formal annual reporting | LCFRB, Port
Taken from the Declaration of Cooperation
Once established, the SLTCRC can provide a forum to:
· develop and pursue an aspirational vision for the whole system
· work together on items that contribute to long-term management of the system and safety and economic well-being of downstream communities
· create a communication venue to exchange information, enhance understanding of system complexities and engage interested parties
· raise awareness of those interested or affected by sediment management in the system
· respond to requests from the U.S. Federal delegation, Washington State Legislature, and the Washington Governor on issues related to managing this complex system

## related agency projects
Other Projects- Information Sharing | Project Description/Link | Point of Contact
Spirit Lake Projects | Spirit Lake Tunnel Intake Gate Replacement and Geotechnical Drilling Project. NEPA complete. Forest Road 99 Extension Improvements implemented in 2022; Gate Replacement implementation anticipated 2023-2026; Geotechnical Drilling implementation anticipated 2024 | USFS - Michele Palmer
| Spirit Lake Outflow Safety Improvement Project: Stay tuned for future updates and public engagement opportunities | USFS - Michele Palmer